## Action plan
ap_number | ap_title | ap_text | success | partners | progress | achieved | hic_number | hic_label | hic_class | timeframe | level | Clarity required
1 | Integrated stop smoking services across the Local Maternity System | Integrated stop smoking services across the Sussex and East Surrey Local Maternity System | Maternity partners across the Sussex and East Surrey Local Maternity System work together to enhance integrated stop smoking support for mothers and families. | Local Maternity System |  |  | 1 | Working in partnership is the building block for success | working_partnership | M | I
2 | Pilot project 'Actively Quitting' using physical activity as a diversion | Pilot project 'Actively Quitting' using physical activity as a diversion | Smokers will be referred from SSS to leisure provision | Arun Wellbeing |  |  | 1 | Working in partnership is the building block for success | working_partnership | S | I
3 | Promote e-cigarettes as a safer and healthier alternative to smoking | Promote e-cigarettes as a safer and healthier alternative to smoking. Work with Public Health 'approved' Vape Shops to give vouchers to bed bound clients | Increase in number of bed bound smokers using E-cigs instead of cigarettes | Fire Service |  |  | 1 | Working in partnership is the building block for success | working_partnership | L | I
4 | Greater sharing of intelligence to Trading Standards | Greater sharing of intelligence to Trading Standards | Increase of intel reports to Trading Standards | Trading Standards |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | S | C/E
5 | Enhanced maternity dataset | Enhanced maternity dataset ensuring smoking status recorded for all pregnant women | All hospitals within the local LMS footprint collect and report data. | Local Maternity System |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | L | I
6 | Improve data capturing from stop smoking services | Improve data capturing from stop smoking services | Improved data quality to understand service delivery and targeting | Public Health |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | S | I
7 | Produce smoking cessation gap analysis and action plan | Produce smoking cessation gap analysis and action plan, based on NICE guidance (PH26) and CLeaR Assessment | Maternity systems demonstrate enhanced stop smoking support and pathways in line with NICE guidance and CLeaR Assessments | Local Maternity System |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | M | C
8 | Report the number of people signposted | Report on the number of people signposted to stop smoking services from wellbeing hubs | Awareness of local smoking population data collected and shared | Worthing Wellbeing, all hubs |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | S/M | C
9 | Share data gathered from health MOTs | Share data gathered from health MOTs to show the number of people identified as smokers | Awareness of local smoking population data collected and shared | Arun Wellbeing |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | S | C
10 | Smoking status recorded for all pregnant women | Smoking status of all pregnant women captured at time of booking and delivery (mandatory) | Accurate data recorded and shared | Maternity at Western Hospitals |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | S | I
11 | Quantify tobacco use by district, age ranges, and ethnicty | Quantify tobacco use by district, age ranges, and ethnicty | Health4Families will be able to target groups to allow appropriate health messages | Health4Families |  |  | 2 | Gather and use the full range of data to inform tobacco control | gather_data | M | C | Q. Is this data you gather that can be shared with others? If so the action needs to change to read share.
12 | Refresh the Health Equity Audit for stop smoking services | Refresh the West Sussex Health Equit Audit for stop smoking services | Completed HEA used to inform servicee redseign | Public Health |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | M | c
13 | Increase understanding of attitudes to smoking among Eastern Europeans | Increase local understanding of attitudes towards smoking among Eastern Europeans in West Sussex | Approriate interventions developed based on insight | Public Health |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | M | C
14 | Support with smokefree prisons | Support Ministry of Justice and Public Health England with smokefree prisons | Improved pathway for those being released from prison to support their smoking cessation | Public Health |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | L | C
15 | Health4Families targetting tobacco related activity | Target Health4Families tobacco related activity at young parents in areas of deprivation | Increase of young parents/people from deprived wards engaging with SSS | Health4Families |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | M | C
16 | Offer targetted workplace health (WPH) services | Target businesses in deprived areas to offer workplace health (WPH) services | Increase in the number of smokers acessing SSS from workplaces deprived areas | Worthing Wellbeing |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | S/M | C
17 | Improving links between prisons and community stop smoking services | Build on national smokefree prisons programme by improving links with the community stop smoking services | A pathway to support those being released from prison estate to continue their stop smoking attempt | Prisons |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | M | C
18 | Use 'Actively Quitting' pilot to target disadvantaged wards | Use 'Actively Quitting' pilot to target disadvantaged wards | Smokers from disadvantaged wards will be referred from SSS to leisure provision | Arun Wellbeing |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | S | C
19 | Uptake of stop smoking services among substance misuse service users | Work with substance misuse services to improve uptake of stop smoking services by service users | Improved pathway for those accesing substance misuse services to support their smoking cessation | Public Health |  |  | 3 | Use tobacco control to tackle health inequalities | health_inequalities | M | I
20 | Actively participate in national and local tobacco control campaigns | Actively participate in national and local tobacco control campaigns | Evaluation of campaign reach, which increases year on year | Arun Wellbeing, Health4Families, Trading Standards, Worthing Wellbeing |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | S/M | C
21 | Annual campaign community event | Actively participate in national and local tobacco control campaigns through at least one annual campaign community event organised by 10 fire stations and through social media | Evaluation of campaign reach, which increases year on year | Fire Service |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | S/M | C
22 | Identify approaches that best serve different communities | Identify approaches to disemminating smokefree messages that best serve different communities | Engagement with BAME groups , particularly Eastern European to gain insight into attitudes towards tobacco use | Communities |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | M | C
23 | Lead on tobacco control communication and campaigns | Lead on tobacco control communication and campaigns | A communication plan for the period of this strategy is produced | Public Health |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | S | E
24 | Provide evidence based information via Family Assist | Provision of evidence based and consistent information, including on smoking cessation, to all families across West Sussex, via an easily accessed and interactive digital platform (Family Assist) | Family Assist achieves high levels of engagement with mothers and families in the provision of comprehensive pre-conception guidance, including on stop smoking information | Western Sussex Hospitals NHS Foundation Trust, Sussex Community NHS Foundation Trust, West Sussex County Council |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | S | C
25 | Distribute 5,000 Safe and Well information booklets | Distribute 5,000 Safe and Well information booklets to residents receiving a Safe and Well visit. Booklets include information on smoking related fires, how to make a home smoke free and where to go for smoking cessation support. | 5,000 booklets will be disctributed to vulnerable people in their homes | Fire Service |  |  | 4 | Deliver Consistent, coherent and coordinated communication | deliver_cccc | S | I
26 | Wellbeing programme that supports tobacco control | Develop the role of the wellbeing programme to support tobacco control | West Sussex wellbeing programmes are more engaged in tobacco control | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | C
27 | Redesign stop smoking service provision in West Sussex | Redesign stop smoking service provision in West Sussex | Effective stop smoking services reaching those that most need to access them | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | L | I
28 | Work with Vape shops to support stop smoking providers in primary care | Work with Vape shops to support stop smoking providers | Improved quit rates. Increased comfidence in stop smoking providers to discuss vaping as a mtehod to quit tobacco | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
29 | Patients are asked about their use of tobacco at pre-assessment clinics | All patients attending pre assessment clinic are asked about their use of tobacco. Smokers are given brief advice and signposted to local stop smoking services | Increase in number of elective patients being signposted to stop smoking services | Western Sussex Hospitals NHS Foundation Trust |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | C
30 | Develop a Patient Group Directive around Champix prescribing | Develop a Patient Group Directive around Champix prescribing | Improved quit rates in phamracy providers | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
31 | improve quality of stop smoking service delivery | improve quality of stop smoking service delivery | Improved conversion rates | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
32 | Improved training offer for stop smoking services | Improve training offer for providers of stop smoking services | Face to face training for new advisors in place and be spoke elearning package for top up training | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
33 | Referral and follow up to stop smoking services | Referral and follow up to stop smoking services whether the stop smoking intervention is inhouse or external | Drop in number of pregnant women still smoking at time of delivery compared to booking | Maternity at Western Hospitals |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
34 | Share data gathered from health MOTs | Share data gathered from health MOTs to show the number of people identified as smokers who have been signposted/referred into SSS | Increase in referrals to SSS | Arun Wellbeing |  |  | 5 | An integrated stop smoking approach | integrated_approach | S | I
35 | Test an integrated midwifery-led stop smoking service | Test an integrated tier 2 midwifery led stop smoking support service | Increase in maternal quit rates between booking and delivery. Shared and integrated learning across Sussex and East Surrey Local Maternity Systems | Local Maternity System |  |  | 5 | An integrated stop smoking approach | integrated_approach | L | I
36 | Preventing ill health from alcohol and tobacco CQUIN | Support NHS achieve the preventing ill health from alcohol and tobacco CQUIN | Local NHS Trusts have achieved the CQUIN | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | M | C
37 | Provide training for primary care staff to deliver stop smoking services | Provide training for primary care staff to deliver stop smoking services | Primary care staff are able to deliver stop smoking services | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S/M/L | I
38 | Work with primary care service providers to improve quantity and quality of services delivered | Work with primary care service providers to improve quantity and quality of services delivered | More stop smoking services within primary care | Public Health |  |  | 5 | An integrated stop smoking approach | integrated_approach | S/M/L | I
39 | Home visiting staff trained in Make Every Contact Count (MECC) | Train Prevention Team home visiting staff in Make Every Contact Count (MECC) | Staff will be more confident in having signposting conversations about smoking cessation and making a record | Fire Service |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
40 | Roll out Make Every Contact Count (MECC) to 30% of operational crews | Work with the Fire and Rescue Training and Development team to roll out Make Every Contact Count (MECC) to 30% of operational crews | 30% of operational personnel will be more confident in having signposting conversations about smoking cessation and recording | Fire Service |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | M | I
41 | A Local Maternity System (LMS) wide action plan | A Local Maternity System (LMS) wide action plan will be developed | Plan developed for use by all organisations which are part of the local LMS. | Local Maternity System |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | C
42 | Carbon monoxide (CO) testing at antenatal appointments | Carbon monoxide (CO) testing at antenatal appointments for all pregnant women | All Pregnant women attending antenatal appointments will be CO tested | Maternity at Western Hospitals |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
43 | Training delivered to all HCP staff involved in the care of pregnant women | Ensure training is delivered to all HCP staff involved in the care of pregnant women in the identification of smoking, delivery of smoking cessation advice and referring to smoking cessation services | Each organisation has training developed and available to relevant workforce. | Local Maternity System |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | M | C
44 | Explore how Dentists could support tobacco control | Explore how Dentists could support tobacco control | Understand the views of dentists to support tobacco control | Public Health |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | L | I
45 | Delivery of smoking brief advice to non-elective inpatients | Improve the delivery of smoking brief advice to non elective inpatients | Non elective inpatients receive appropriate advice and support to stop smoking | Western Sussex Hospitals NHS Foundation Trust |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | M | I
46 | Rollout Make Every Contact Count programme to clinical and non-clinical staff | Rollout Make Every Contact Count (MECC) programme to clinical and non-clinical staff in healthcare settings such as primary care | Increased confidence of front line staff in raising the issue of smoking | Public Health |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | M | I
47 | Signpost smokers to stop smoking services | Signpost smokers to stop smoking services when conducting Safe and Well visits | Increase in the number of people accessing the SSS | Fire Service |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
48 | Health4Families staff training | Health4Families staff to complete National Centre for Smoking Cessation and Training Very Brief Advice level 1 training. | 1. All staff will be VBA trained, 2. Staff will be confident to discuss smoking cessation and record conversation outcome | Health4Families |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I | Q. you mentioned that staff are audited every 6 months what does this mean and what is in the audit
49 | Wellbeing hub staff level 1 training | Wellbeing hub staff to complete National Centre for Smoking Cessation and Training Very Brief Advice level 1 trianing. | 1. All wellbeing staff will be VBA trained, 2. Wellbeing staff will be confident to discuss smoking cessation and record conversation outcome | All hubs |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
50 | Wellbeing hub staff level 2 training | Wellbeing hub staff to complete National Centre for Smoking Cessation and Training Very Brief Advice level 2 trianing. | 1. All wellbeing staff will be VBA trained, 2. Wellbeing staff will be confident to discuss smoking cessation and record conversation outcome | All hubs |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
51 | Midwives level 1 training | Midwives to complete National Centre for Smoking Cessation and Training Very Brief Advice on smoking for pregnant women level 1 to talk about smoking cessation with pregnant women and their partners | 1. All midwives will be VBA trained, 2. Midwives will be confident to discuss smoking cessation and record conversation outcome | Maternity at Western Hospitals |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | S | I
52 | Safe and Well visits to test individual levels of carbon monoxide | Use carbon monoxide (CO) Monitors during Safe and Well Visits to test individual levels of CO | Identify people who have high levels of CO in their breath and to raise awareness of the impact from smoking | Fire Service |  |  | 6 | Build and sustain capacity in tobacco control | build_sustain_capacity | L | I
53 | Disrupt the supply of illicit tobacco | Continue to disrupt the supply of illicit tobacco in West Sussex | More traders brought into compliance, increase in numbes of seizures and quantities seized | Trading Standards |  |  | 7 | Tackle cheap and illicit tobacco | tackle_cheap_illicit_tob | S/M/L | C/E | Q. Can any of these be broken down into short medium or long term or are they all S/M/L term?
54 | Educate consumers of illicit tobacco | Educate consumers of issues with illicit tobacco and how to report it | Increase in intelligence and intel reported | Trading Standards |  |  | 7 | Tackle cheap and illicit tobacco | tackle_cheap_illicit_tob | S/M/L | C/E | Q. Can any of these be broken down into short medium or long term or are they all S/M/L term?
55 | Clear reporting mechanisms for illicit tobacco among midwives | If staff are aware that illicit tobacco is being used they know how to report | Increase in the number of IT reports to Trading Standards | Maternity at Western Hospitals, Arun Wellbeing, Health4Families, Worthing Wellbeing |  |  | 7 | Tackle cheap and illicit tobacco | tackle_cheap_illicit_tob | S | C
56 | Review Smoke Free West Sussex Partnership membership | Review Smoke Free West Sussex Partnership membership | A partnership that actively discusses and addresses through working together the tobacco issues in West Sussex | Public Health |  |  | 8 | Influence change through advocacy | advocacy | S | E
57 | CLeaR deep dive | Complete a CLeaR model (Challenge, Leadership and Results) deep dive for Smokefree West Sussex | Recommendations to develop SFWSP | Public Health |  |  | 8 | Influence change through advocacy | advocacy | M | E
58 | Link messages into community and voluntary sector organsiations | Link messages regarding tobacco control into community and voluntary sector organsiations | Communities team raise tobacco control at a minimum of two events per year | Communities |  |  | 8 | Influence change through advocacy | advocacy | S | C
59 | Link tobacco control messages into directorate team meetings | Link messages regarding tobacco control into directorate team meetings | Tobacco control raised at a mnimum of two C&PP directorate management team meetings a year | Communities |  |  | 8 | Influence change through advocacy | advocacy | S | C
60 | Raise the issue of tobacco control in West Sussex | Support members and the Director of Public Health in West Sussex to raise the issue of tobacco control | Whole system approaches to tobacco control embedded and health in all policies include tobacco control | Public Health |  |  | 8 | Influence change through advocacy | advocacy | L | E
61 | Under age sales operations on intel led targets | Continue to undertake under age sales operations on intel led targets | Reduction in 'hit rates' of sales in UAS operations | Trading Standards |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | S/M/L | I/C/E | Q. Can any of these be broken down into short medium or long term or are they all S/M/L term?
62 | Educating businesses in under age sales legislation | Educate businesses in West Sussex in under age sales legislation | Increased number of businesses with knowledge of UAS legislation and engagment with TS | Trading Standards |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | S/M/L | I/C/E | Q. Can any of these be broken down into short medium or long term or are they all S/M/L term?
63 | Understanding attitudes to smoking among young people in West Sussex | Increase local understanding of attitudes to smoking of young people in West Sussex | Approriate interventions developed based on insight | Public Health |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | M | C
64 | Signpost Health4Families service users to stop smoking services | Referring young people who use Health4Families who are smokers to stop smoking services | Increase number of young people engaging with stop smoking services | Health4Families |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | S | I
65 | Support the Local Maternity System | Support the Local Maternity System to achieve its aspirations related to tobacco control | LMS has achieved its aspirations | Public Health |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | M | I
66 | Young parents care pathway | Use young parents care pathway as an opportunity to advise on health messages | Fewer young parents smoking at time of delivery | Maternity at Western Hospitals |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | S | I
67 | Investigate efficacy of interventions for young people | Investigate efficacy of prevention and smoking cessation interventions for young people | Awareness of appropriate interventions for preventing the uptake of smoking among young people as well as helping them stop. This will be through a review of published and grey literature and other social research methods. | Public Health |  |  | 9 | Helping young people to be tobacco free | yp_smokefree | M | I
68 | Local Maternity System knowledgebase | Information on effects of smoking/smoking cessation services/smoke free homes included on LMS knowledgebase. | Increase in visits/hits to knowledgebase per year. | Local Maternity System |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments |  | I
69 | Nicotine Replacement Therapy available during hospital stay | Nicotine Replacement Therapy (NRT) to be available to all pregnant women during hospital stay | An increase in the number of pregnant women on NRT during their hospital stay | Maternity at Western Hospitals |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments | S | I
70 | Review workplace smokefree policies for local authorities | Review the smokefree policy for local authorities | Evidence based workplace policy in WSCC | Public Health |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments | M | C
71 | Health4Families Smokfree policy | Develop a Smokfree policy for all service buildings and areas staff can use whilst at work | All Children and family centres adhere to smokefree policy | Health4Families |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments | S | E | Q. is there a policy already in place, what specifically is the action/objective here?
72 | Promoting smokefree environments outside maternity units | Training staff to maintain and promote smoke free environment outside maternity unit | Smoke Free maternity grounds | Maternity at Western Hospitals |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments | M | E
73 |  | Explore how planning and licensing processes in District and Boroughs can be utilised to promote smokefree environments | Smoke Free environments promoted | Public Health |  |  | 10 | Maintain and promote smoke free enviornments | smokefree_environments | M | E